## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a project team, I want to upload PDF, DOCX, TXT and CSV project documents so that all project information can be collected. | Must | Python file parsers; Streamlit uploader | Keerthi | Completed
Sprint 1 | Sprint 1 | US-02 | As a project team, I want uploaded documents to be chunked, embedded and indexed so that project information can be retrieved using RAG. | Must | Document ingestion module | Keerthi | Completed
Sprint 1 | Sprint 1 | US-03 | As a project team, I want a unified project knowledge base so that information from different document formats can be searched in one place. | Must | US-01, US-02 | Keerthi | Completed
Sprint 2 | Sprint 2 | US-04 | As a project manager, I want the system to extract project goals, milestones, timelines and responsibilities so that project scope and deliverables are clear. | Must | RAG knowledge base | Keerthi | In Progress
Sprint 2 | Sprint 2 | US-05 | As a project manager, I want the system to detect schedule risks, dependency gaps and delivery challenges so that risks can be addressed early. | Must | US-03, project documents | Keerthi | In Progress
Sprint 2 | Sprint 2 | US-06 | As a project manager, I want the system to identify blockers, pending decisions and action items so that unresolved work can be tracked. | Must | Meeting notes and progress updates | Keerthi | In Progress
Sprint 2 | Sprint 2 | US-07 | As a developer, I want to validate all three agents using PDF, DOCX, TXT and CSV samples so that the outputs are reliable across formats. | Should | US-04, US-05, US-06 | Keerthi | Planned
Sprint 3 | Sprint 3 | US-08 | As a project team, I want the system to generate user stories, a risk register, and structured action-item lists from project content. | Must | Milestone 2 agents and RAG knowledge base | Keerthi | Planned
Sprint 3 | Sprint 3 | US-09 | As a project manager, I want an overall project health score with dimension-wise breakdown so that I can understand project health. | Must | Scope, risk and blocker outputs | Keerthi | Planned
Sprint 3 | Sprint 3 | US-10 | As a project team member, I want a conversational assistant to answer project questions using uploaded documents. | Must | RAG knowledge base and agent outputs | Keerthi | Planned
Sprint 3 | Sprint 3 | US-11 | As a project team member, I want conversational answers validated for accuracy and relevance against uploaded documents. | Should | US-10 and source documents | Keerthi | Planned
Sprint 4 |  | US-12 | High |  |  |  | Planned
Sprint 4 |  | US-13 | High |  |  |  | Planned
Sprint 4 |  | US-14 | Medium |  |  |  | Planned
Sprint 4 |  | US-15 | Medium |  |  |  | Planned
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-01 | T1.1 | Create Streamlit document upload interface | Week 1 | Week 1 | Keerthi S | Development | Completed | 2 | Day 1: 2
US-01 | T1.2 | Implement PDF and DOCX text extraction | Week 1 | Week 1 | Keerthi S | Development | Completed | 2 | Day 2: 2
US-01 | T1.3 | Implement TXT and CSV file readers | Week 1 | Week 1 | Keerthi S | Development | Completed | 1.5 | Day 3: 1.5
US-02 | T1.4 | Implement document chunking with configurable size and overlap | Week 1 | Week 2 | Keerthi S | Development | Completed | 2 | Day 4: 2
US-02 | T1.5 | Generate embeddings and build vector index | Week 2 | Week 2 | Keerthi S | Development | Completed | 2 | Day 5: 2
US-03 | T1.6 | Build unified project knowledge base and retrieval pipeline | Week 2 | Week 2 | Keerthi S | Integration | Completed | 1.5 | Day 6: 1.5
SPRINT 2 BACKLOG
US-04 | T2.1 | Develop Scope and Deliverable Extraction Agent | Week 3 | Week 3 | Keerthi S | Development | In Progress | 2 | Day 1: 2
US-04 | T2.2 | Extract project goals, milestones, timelines and responsibilities | Week 3 | Week 3 | Keerthi S | Development | In Progress | 2 | Day 2: 2
US-05 | T2.3 | Develop Risk Detection and Delivery Forecasting Agent | Week 3 | Week 4 | Keerthi S | Development | In Progress | 2.5 | Day 3: 2.5
US-05 | T2.4 | Identify schedule risks, dependency gaps and delivery challenges | Week 4 | Week 4 | Keerthi S | Development | In Progress | 2 | Day 4: 2
US-06 | T2.5 | Develop Blocker and Action Item Identification Agent | Week 4 | Week 4 | Keerthi S | Development | In Progress | 2 | Day 5: 2
US-06 | T2.6 | Extract pending decisions, unresolved issues and assigned actions | Week 4 | Week 4 | Keerthi S | Development | In Progress | 2 | Day 6: 2
US-07 | T2.7 | Validate all agents using PDF, DOCX, TXT and CSV samples | Week 4 | Week 4 | Keerthi S | Testing | Planned | 1.5 | Day 7: 1.5
SPRINT 3 BACKLOG
US-08 | T3.1 | Develop Documentation Generation Agent | Week 5 | Week 5 | Keerthi S | Development | Planned | 2 | Day 1: 2
US-08 | T3.2 | Generate user stories, risk register and structured action-item lists | Week 5 | Week 5 | Keerthi S | Development | Planned | 2.5 | Day 2: 2.5
US-09 | T3.3 | Develop Project Health Scoring Module | Week 5 | Week 6 | Keerthi S | Development | Planned | 2 | Day 3: 2
US-09 | T3.4 | Calculate scope clarity, timeline risk and blocker-count dimensions | Week 6 | Week 6 | Keerthi S | Development | Planned | 2 | Day 4: 2
US-10 | T3.5 | Implement RAG-powered Conversational Project Intelligence Assistant | Week 6 | Week 6 | Keerthi S | Development | Planned | 2.5 | Day 5: 2.5
US-10 | T3.6 | Add document-grounded responses for project status and risk questions | Week 6 | Week 6 | Keerthi S | Integration | Planned | 2 | Day 6: 2
US-11 | T3.7 | Validate conversational assistant accuracy and relevance against uploaded documents | Week 6 | Week 6 | Keerthi S | Testing | Planned | 2 | Day 7: 2
SPRINT 4 BACKLOG
US-12 | T4.1 | Review and fix unresolved blocker extraction rules | Week 7 | Week 7 | Keerthi S | Development | Planned | 2 | Day 1: 2
US-12 | T4.2 | Test blocker detection and exclude resolved or closed issues | Week 7 | Week 7 | Keerthi S | Testing | Planned | 1.5 | Day 1: 1.5
US-13 | T4.3 | Implement and validate pending-decision and approval detection | Week 7 | Week 7 | Keerthi S | Development | Planned | 2 | Day 1: 2
US-14 | T4.4 | Improve RACI responsibility extraction and dashboard display | Week 8 | Week 8 | Keerthi S | Development | Planned | 2 | Day 1: 2
US-15 | T4.5 | Verify dashboard counts, duplicate handling and PDF/DOCX/TXT/CSV outputs | Week 8 | Week 8 | Keerthi S | Testing | Planned | 2.5 | Day 1: 2.5
US-15 | T4.6 | Run regression tests and update project documentation with test evidence | Week 8 | Week 8 | Keerthi S | Testing / Documentation | Planned | 2 | Day 1: 2
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Need to finalize supported document formats and extraction approach. | Reviewed PDF, DOCX, TXT and CSV ingestion plan.
Sprint 1 | Day 5 | Embedding and vector index integration required testing. | Indexed sample project documents and checked chunk count.
Sprint 2 | Day 1 | Agent prompts and output structure need to be defined. | Defined three agent responsibilities and structured outputs.
Sprint 2 | Day 5 | Validation requires representative files in all four formats. | Prepared sample files and validation checks for each format.
Sprint 3 | Day 1 | Documentation generation output structure needs to be finalized. | Defined templates for user stories, risk register and action-item lists.
Sprint 3 | Day 3 | Health score dimensions need consistent calculation. | Defined scoring inputs for scope clarity, timeline risk and blocker count.
Sprint 3 | Day 5 | Assistant answers must remain grounded in uploaded documents. | Tested RAG-based questions and compared answers with source content.
Sprint 4 | Day 1 | Review blocker and pending-decision detection; assign fixes. | Keerthi S | Planned
Sprint 4 | Day 3 | Validate RACI extraction and dashboard counts with sample documents. | Keerthi S | Planned
Sprint 4 | Day 5 | Run regression tests, record results, and update documentation. | Keerthi S | Planned

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | Week 1 | Week 2 | Keerthi | Start documenting ingestion and RAG decisions after each development task. | Stop testing only one document format. | Continue modular development and regular indexing checks. | Added multi-format ingestion, chunking, embeddings and vector indexing.
2 | Sprint 2 | Week 3 | Week 4 | Keerthi | Start maintaining evidence-based agent outputs and validation cases. | Stop treating extracted information as valid without checking source evidence. | Continue using modular agents and testing with realistic project documents. | Implemented scope, risk, blocker/action agents and prepared multi-format validation.
3 | Sprint 3 | Week 5 | Week 6 | Keerthi | Start validating generated documentation and health scores with source evidence. | Stop accepting conversational answers without checking document grounding. | Continue modular agent development and RAG-based validation. | Planned documentation generation, project health scoring, conversational assistant, and assistant accuracy validation.
4
5
6
7
Sprint 4 | What went well: blocker and decision parsing improved. What to improve: validate against more real project documents. | Planned | Add parser tests and confirm dashboard counts against extracted records.