## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Keerthi S | 01-Sep-2026 | PDF text extraction did not preserve the original document formatting. | Sprint 1 | Keerthi S | Others | Updated the extraction/display handling so the extracted text is shown clearly. | 01-Sep-2026 | Closed | Verified after correction.
2 | Keerthi S | 02-Sep-2026 | CSV file content was not displayed correctly during document extraction. | Sprint 1 | Keerthi S | Logical | Corrected CSV reading and verified the extracted content. | 02-Sep-2026 | Closed | Verified with CSV file.
3 | Keerthi S | 03-Sep-2026 | TXT file extraction required correction of line-break handling for clear display. | Sprint 1 | Keerthi S | User Interface | Adjusted the text display to retain readable line breaks. | 03-Sep-2026 | Closed | Verified with TXT file.
4 | Keerthi S | 10-Sep-2026 | Scope and Deliverable Extraction Agent did not extract responsibilities from some project documents. | Sprint 2 | Keerthi S | Logical | Improved the extraction prompt and added responsibility-related keywords and checks. | 10-Sep-2026 | Closed | Retested with project proposal and meeting notes.
5 | Keerthi S | 11-Sep-2026 | Risk Detection Agent missed dependency gaps when the dependency information appeared in meeting notes. | Sprint 2 | Keerthi S | Logical | Updated risk-detection rules to identify dependency-related phrases and connect them with delivery risks. | 11-Sep-2026 | Closed | Verified using meeting notes and progress updates.
6 | Keerthi S | 12-Sep-2026 | Blocker and Action Item Agent did not consistently identify pending decisions and assigned action items. | Sprint 2 | Keerthi S | Logical | Refined action-item extraction and added fields for blocker, owner, due date, and pending decision. | 12-Sep-2026 | Closed | Verified with sample meeting notes.
7 | Keerthi S | 15-Sep-2026 | Multi-format validation initially produced inconsistent outputs across PDF, DOCX, TXT, and CSV files. | Sprint 2 | Keerthi S | Others | Standardized the agent output format and added validation checks for all supported document types. | 15-Sep-2026 | Closed | Validation completed for all four formats.
8 | Keerthi S | 22-Sep-2026 | Documentation Generation Agent did not generate complete user stories, risk register, and structured action-item lists from all ingested project content. | Sprint 3 | Keerthi S | Logical | Refined the documentation-generation logic and output structure to include the required fields for user stories, risk register, and action items. | 22-Sep-2026 | Closed | Retested with ingested project documents.
9 | Keerthi S | 23-Sep-2026 | Project Health Scoring Module did not consistently reflect all required dimensions: scope clarity, timeline risk, and blocker count. | Sprint 3 | Keerthi S | Logical | Updated the health-score calculation to process each dimension separately and combine them into an overall project health score. | 23-Sep-2026 | Closed | Verified dimension-wise scoring.
10 | Keerthi S | 24-Sep-2026 | Conversational Project Intelligence Assistant returned incomplete answers for some project questions. | Sprint 3 | Keerthi S | Logical | Improved RAG retrieval and response handling so answers are grounded in relevant uploaded project documents. | 24-Sep-2026 | Closed | Tested questions such as project status and major risks.
11 | Keerthi S | 25-Sep-2026 | Conversational assistant responses were not consistently accurate or relevant to the uploaded document content during validation. | Sprint 3 | Keerthi S | Others | Added validation cases comparing assistant responses with the relevant uploaded-document content and refined retrieval/response handling. | 25-Sep-2026 | Closed | Accuracy and relevance checked against source documents.
12 | Keerthi S | 26-Sep-2026 | Blockers & Action Items dashboard showed zero unresolved blockers even when blocker-related statements were present in the uploaded project notes. | Sprint 4 | Keerthi S | Logical | Improved blocker keyword matching and status normalization, then connected the extracted blocker records to the dashboard metrics. | 26-Sep-2026 | Closed | Retested with sample notes containing open and resolved blockers.
13 | Keerthi S | 27-Sep-2026 | Pending Decisions section did not identify decision-required and awaiting-approval statements in meeting notes. | Sprint 4 | Keerthi S | Logical | Extended pending-decision pattern matching and excluded decisions marked approved or completed. | 27-Sep-2026 | Closed | Verified pending and completed decision examples.
14 | Keerthi S | 28-Sep-2026 | RACI Matrix extraction missed responsibility assignments when role and RACI type were written in plain-text format. | Sprint 4 | Keerthi S | Logical | Updated RACI parsing for role-based responsibility lines and normalized Accountable, Responsible, Consulted, and Informed labels. | 28-Sep-2026 | Closed | Validated against TXT and DOCX responsibility examples.
15 | Keerthi S | 29-Sep-2026 | Blocker and pending-decision counts could become inconsistent with the records displayed in the dashboard. | Sprint 4 | Keerthi S | Logical | Used the same filtered blocker and decision collections for both summary counts and dashboard tables. | 29-Sep-2026 | Closed | Checked that summary totals match displayed records and resolved items are excluded.

## Sheet2
Logical | Milestone 2 defects added for Sprint 2
User Interface | Milestone 3 defects added for Sprint 3
Maintainability | Milestone 4 defects added for Sprint 4
Standards
Others